### Activity Plan Work plan item Short stories

Responsible SAI: IDI and Liberia as co-lead

|  |  |  |
| --- | --- | --- |
| **Activity** | **When** | **Comment** |
|  |  |  |
| Define briefly what is meant as short stories.  This is not necessarily about best practice, but possibly more about good practice. The stories should especially be linked to being a SAI in a situation of fragility. | February |  |
| Invite working group members and the forum to contribute stories, such as during the meeting in Pretoria in March. | March | Is it ok to allocate about 30 mins for this during the meeting in Pretoria in March? |
| Ask for short stories from INTOSAI providers of support (SAIs and regional organizations), incl IDI programmes and the material collected by the INTOSAI Donor Secreatariat | March-April | Need to clarify which SAIs should be asked |
| Compile short stories and send them for review in the | April-May |  |
| Publisize and share short stories in various in different media; CBC webpage and newsletter, others? | Ongoing |  |
| Consider to repeat collection of short stories in 2019 |  |  |