## sheet 1
Revision of ISSAI 5600
updated August 2015
Milestones | 2012 |  |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016
| 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
[9 empty] | SC 3 meeting Bratislava, Slovakia | [26 empty] | CBC and CBC Steering Committee - Stockholm. Sweden
1. Analyse the needs/expectations of SAIs | [23 empty] | CBC meting Lima, Peru
- Gather feedback from SAIs
- Analyse needs and expectations of SAIs
2. Overall direction of ISSAI 5600
- Define purpose of PR Guide and Checklist
- Consider possible effects of new ISSAIs/PMF
3. Structure and content of ISSAI 5600
- Include experiences/lessons learned
- Include good practice examples
- Include references to ISSAIs and the PMF
- Include references to other relevant material
- SC 3 agrees on structure and content
4. (Re-) Write Chapters of ISSAI 5600 (1st draft)
- Task Team provides 1st draft
- SC 3 members comment on 1st draft
- Task Team incorporates comments (2nd draft)
5. Exposure Draft
- SC 3 members comment on 2nd draft
- Task Team incorporates comments (3rd draft)
- SC 3 members agree upon 3rd draft
- CBC Steering Committee approves Exposure Draft
6. Prepare Endorsement Version | [50 empty] | INCOSAI
- Exposure period
- Incorporate comments (4th draft)
- translation
7. INCOSAI 2016 approves revised ISSAI 5600