## Slide 1: High level work plan of the Workstream on Guides and Occasional Papers
For the period 2020-22

## Slide 2: Workstream on Guides and Occasional Papers
Performance / progress indicator | Start and end dates | Funding source
Identify areas where new guides may be needed | Jan 2020- June 2022 | Workstream members in-kind support
Develop a strategy to encourage SAIs to volunteer to take up the responsibility of developing new guides | Current to June 2020 | 
Identify the guides to be translated and find SAIs to assist in proof reading the translations | Jan. 2020-Dec. 2020 | Workstream members and CBC Budget
Develop strategies to popularise and increase the use of guides and occasional papers and blogs | Current to June 2021 | Workstream members in-kind support
Initiative / activity planned | Link to CBC strategy
Developing and maintaining CBC guides and Occasional papers and other resources | Strategic Objective 2, Key strategy 5

## Slide 3: Workstream on Guides and Occasional Papers
Performance / progress indicator | Start and end dates | Funding source
Identify guides which need updating- target two per year | Current to June 2022 | Workstream members in-kind support
Proactively encourage SAIs to volunteer to take up the responsibility of updating the guides | August 2019- June 2020 | 
Develop strategies to encourage SAIs to contribute blogs | August 2019- June 2020 | 
Initiative / activity planned | Link to CBC strategy
Developing and maintaining CBC guides and Occasional papers and other resources | Strategic Objective 2, Key strategy 5